## Summary
PL Data Management Tool (PL-DMT) Description The PL Data Management Tool is built with the below key objectives. 1. Keep SE & SO data up to date for review and communication 2. Help RM monitor SE & SO data updates and mark attendance for work monitoring 3. Enable the Admin team to manage backend activities like new additions, removals and hierarchy mapping at a central place. Web Server Requirements Operating System: Ubuntu 16+ Web Server: Lampp PHP Version: PHP 5.6+ Database: MySQL 5.7 Technology PHP MVC Framework Codeignitor Bootstrap Theme Jquery

## ProjectPlan
PL Data Management Tool | [57 empty] | [42]
Next Wealth
|  |  | Project Start: | 2019-07-24
| Project Manager: |  | Display: | Daily
|  |  | Display Period: | 1 | time axis 2019-07-24 to 2019-09-16
| Prabhu Velusamy Jayanth Samparthi | Development Lead: | Ragunathan C | [6 empty] | 24 Jul '19 | 25 Jul '19 | 26 Jul '19 | 27 Jul '19 | 28 Jul '19 | 29 Jul '19 | 30 Jul '19 | 31 Jul '19 | 1 Aug '19 | 2 Aug '19 | 3 Aug '19 | 4 Aug '19 | 5 Aug '19 | 6 Aug '19 | 7 Aug '19 | 8 Aug '19 | 9 Aug '19 | 10 Aug '19 | 11 Aug '19 | 12 Aug '19 | 13 Aug '19 | 14 Aug '19 | 15 Aug '19 | 16 Aug '19 | 17 Aug '19 | 18 Aug '19 | 19 Aug '19 | 20 Aug '19 | 21 Aug '19 | 22 Aug '19 | 23 Aug '19 | 24 Aug '19 | 25 Aug '19 | 26 Aug '19 | 27 Aug '19 | 28 Aug '19 | 29 Aug '19 | 30 Aug '19 | 31 Aug '19 | 1 Sep '19 | 2 Sep '19 | 3 Sep '19 | 4 Sep '19 | 5 Sep '19 | 6 Sep '19 | 7 Sep '19 | 8 Sep '19 | 9 Sep '19 | 10 Sep '19 | 11 Sep '19 | 12 Sep '19 | 13 Sep '19 | 14 Sep '19 | 15 Sep '19 | 16 Sep '19
WBS | TASK DESCRIPTION | ASSIGNED TO | PROGRESS | PLAN START | PLAN END | PLAN DAYS | ACTUAL START | ACTUAL END | ACTUAL DAYS | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54
Phase 1 Title
| Requirement and Analysis | Ramachandiran | 0% | 2019-07-26 | 2019-07-26 | 1
| Database Design | Ramachandiran | 0% | 2019-07-29 | 2019-07-29 | 1
| OTP Login Procedure, Authentication | Manikandan | 0% | 2019-07-30 | 2019-07-31 | 2
| Manage menu permission for each Role | Manikandan | 0% | 2019-08-01 | 2019-08-01 | 1
| RM Module (Form Design and Validation, EDIT, APPROVAL and SMS) | Manikandan | 0% | 2019-08-02 | 2019-08-06 | 3
| SE Module (Field Validation, EDIT and SMS) | Manikandan | 0% | 2019-08-07 | 2019-08-09 | 2
| SO Module (Field Validation, EDIT and SMS) | Manikandan | 0% | 2019-08-12 | 2019-08-12 | 1
| Team Management (Deactivate, Remove, Team Changing and SMS) | Manikandan | 0% | 2019-08-13 | 2019-08-16 | 4
| ADMIN: UI Designing, Login, Approvals for Deactivation of SEs | Ramachandiran | 0% | 2019-07-26 | 2019-07-29 | 2
| ADMIN: Manage (SE/ SO /RM Data, RHS, Values of Product/ Hierarchy/ Long Leave/ Deactivation Reason) | Ramachandiran | 0% | 2019-07-30 | 2019-08-02 | 3
| ADMIN: Reports (SE Exception, SE Changes, SE on Long Leave) | Ramachandiran | 0% | 2019-08-05 | 2019-08-06 | 2
| ADMIN: Uploads / Download (SE/ SO/ RM List) | Ramachandiran | 0% | 2019-08-07 | 2019-08-09 | 3
| Testing | Ram & Mani | 0% | 2019-08-19 | 2019-08-22 | 4
Phase 2 Title
| UI Design (Responsive for Both ADMIN and RM pages) | Manikandan | 0% | 2019-08-26 | 2019-08-27 | 2
| Attendance Module | Manikandan | 0% | 2019-08-28 | 2019-08-30 | 3
| Attendance Reports | Manikandan | 0% | 2019-09-02 | 2019-09-02 | 1
| Phase1 Integration | Ram & Mani | 0% | 2019-09-03 | 2019-09-04 | 2

## Database
TABLE | FIELD | COMMENTS
ATTENDANCE VALUE | value_no
| attendance_value | P, A, L, etc
| description | P = Present, L = Leave, etc
| color_code | Color code to each value for differentiate
| created_on | CURRENT_TIMESTAMP
| status | 1 = Active, 0 = In-active
LEAVE REASON | reason_no
| reason | Maternity, Long Leave etc
description
| created_on | CURRENT_TIMESTAMP
| status | 1 = Active, 0 = In-active
PRODUCT | product_no
| product | Sales, Education Loan, etc
description
| created_on | CURRENT_TIMESTAMP
created_by
| status | 1 = Active, 0 = In-active
DEACTIVATED REASON | s_no
| reason | Resigned/ Absconding/ Not joined
description
| created_on | CURRENT_TIMESTAMP
| status | 1 = Active, 0 = In-active
DESIGNATION | s_no
| designation | Admin / RM / SO / SE
description
| created_on | CURRENT_TIMESTAMP
created_by
| status | 1 = Active, 0 = In-active
EMPLOYEE | s_no
employee_id
first_name
last_name
| designation | (Admin/ RM /SO /SE) from designation table
email
mobile1
mobile2
mobile3
photo
| c_code | Should start with C
| ban_id | Should start with BAN
| vsts_id | Should start with IPRO or CODE NA
| product | Product name from product table (Ex: Sales, etc)
modified_on
modified_by
| created_on | CURRENT_TIMESTAMP
created_by
| status | 1 = Active, 0 = In-active
MANAGER TRACKER | s_no
employee_id
| level1_mgr | Employee ID from this table
| level2_mgr | Employee ID from this table
modified_on
modified_by
| created_on | CURRENT_TIMESTAMP
created_by
| status | 1 = Active, 0 = In-active
OTP Validation | employee_id | Employee ID
| designation | Admin / RM / SO / SE
otp
| created_on | CURRENT_TIMESTAMP
| status | 1 = Active, 0 = In-active
ACCESS TRACKER | s_no
| employee_id | Employee ID
| designation | Admin / RM / SO / SE
| employee_name | (SE/SO/RM/Admin)
| access_type | (Login/Logout)
| created_on | CURRENT_TIMESTAMP
| status | 1 = Active, 0 = In-active
EMPL DATA CHANGE TRACKER | s_no
| employee_id | Employee ID
| change_type | RM/ SOL_ID
| changed_by | Admin / RM / SO / SE
field_name
old_value
new_value
| approved | Y / N
| approval_by | Employee(RM) ID
| created_on | CURRENT_TIMESTAMP
| status | 1 = Active, 0 = In-active
Empl Status Changes Tracker | s_no
| change_type | Remove / Deactivation
| changed_by | Employee(RM) ID
employee_id
| new_rm | Employee(New RM) ID
reason
| approved | Y / N
| approval_by | Employee(RM) ID
| created_on | CURRENT_TIMESTAMP
| status | 1 = Active, 0 = In-active
Empl SOL ID Mapping | s_no
employee_id
Branch SOL ID
| created_on | CURRENT_TIMESTAMP
| status | 1 = Active, 0 = In-active
Empl Attendance Tracker | employee_id
month_year
day1
day2
:
day31
| created_on | CURRENT_TIMESTAMP
| status | 1 = Active, 0 = In-active
Empl Leave Tracker | s_no
employee_id
Leave Start Dt
Leave End Dt
Leave Reason
| approved | Y / N
| approval_by | Employee(RM) ID
| created_on | CURRENT_TIMESTAMP
| status | 1 = Active, 0 = In-active
Admin Usage Tracker | s_no
employee_id
| Type of Activity | (Report/Download/Upload/Approval/Data)
Activity Name
| created_on | CURRENT_TIMESTAMP